## Manual Test
Manual & Automation Testing Training Schedule
Week | Duration | Chapter | Training Outline | Content | Duration |  | Objectives | Training Method | Start date | Finish date | Progress | Notes
[5 empty] | Plan (hour) | Actual (hour)
1 |  | 1 | Software Testing Overview | Introduction to Software Testing | 2 |  | Get knowledge about basic theory of testing | Mentor |  |  |  | http://tryqa.com/ https://www.guru99.com https://www.tutorialspoint.com/software_testing/
|  |  |  | Objectives of Testing | 2 |  |  | Seft-training
|  |  |  | Software Development Process | 2 |  |  | Seft-training
|  |  |  | Principle of testing | 2 |  |  | Seft-training
|  |  |  | Error / Fault / Failure | 2 |  |  | Seft-training
|  |  |  | What is Verification & Validation | 2 |  |  | Seft-training
|  |  |  | Difference between QA & QC | 2 |  |  | Mentor
|  |  | Software Development Life Cycle (SDLC) | SDLC Phases | 2 |  | Understand the Agile model with the rest | Seft-training
|  |  |  | SDLC Models: Water Fall | 2 |  |  | Seft-training
|  |  |  | SDLC Models: V Model | 2 |  |  | Seft-training
|  |  |  | SDLC Models: Agile Model | 5 |  |  | Mentor
|  |  |  | Scrum Methodology | 5 |  |  | Mentor
|  |  |  | Kanban Methodology | 2 |  |  | Mentor
2 |  |  | Software Testing Type | Manual testing | 2 |  | Understand the testing type | Seft-training
|  |  |  | Automation testing | 2 |  |  | Seft-training
|  |  | Software Testing Methodologies | Static Testing | 2 |  | Understand the testing methodology | Seft-training
|  |  |  | Dynamic Testing | 2 |  |  | Seft-training
|  |  |  | White Box Testing | 2 |  |  | Seft-training
|  |  |  | Black Box Testing | 2 |  |  | Seft-training
|  |  |  | Gray Box Testing | 2 |  |  | Seft-training
|  |  |  | Presentation 1: Software Development Life Cycle, Software Testing Type, Software Testing Methodologies | 2 |  |  | Sharing meeting
|  | 2 | Software Testing Levels | Unit Testing | 4 |  | Understand the testing level | Seft-training
|  |  |  | Integration Testing | 4 |  |  | Seft-training
|  |  |  | System Testing | 8 |  |  | Mentor
|  |  |  | Acceptance Testing | 2 |  |  | Mentor
3-4 |  |  | Test case Design Technique | Specification-based techniques | 4 |  | Able to create testcase after read specs | Mentor
|  |  |  | Experience-based techniques. | 2 |  |  | Mentor
|  |  |  | Practice on real project: | 34 |  |  | Seft-training
5-6 |  |  | Bug Life Cycle | Explain bug life cycle | 8 |  | Write bug on system and follow it to the end of its life cycle | Mentor
|  |  |  | Report bug on Redmine, Trello | 8 |  |  | Mentor
|  |  |  | Practice on real project: | 22 |  |  | Seft-training
|  |  |  | Presentation 2: Software Testing Levels, Test case Design Technique, Bug Life Cycle | 2 |  |  | Sharing meeting
7-9 |  | 3 | Project | Read and Analyze SRS | 18 |  | Understand and apply the knowledge in the product | Seft-training
|  |  |  | Create Testcase | 24 |  |  | Seft-training
|  |  |  | Run + Update Testcase | 8 |  |  | Seft-training
|  |  |  | Execute manual testing | 40 |  |  | Seft-training
|  |  |  | Report bug on Redmine | 30 |  |  | Seft-training
10 |  | 4 | TypeScript | What is Type Script? | 1 |  | Get knowledge TypeScript | Seft-training
|  |  |  | Install TypeScript | 1 |  |  | Seft-training
|  |  |  | TypeScript Basic Types | 6 |  |  | Seft-training
|  |  |  | If Else, and Switch Case in TypeScripts | 6 |  |  | Seft-training
|  |  |  | Loop in TypeScripts | 6 |  |  | Seft-training
|  |  |  | Class and object | 6 |  |  | Seft-training
|  |  |  | Async and await | 6 |  |  | Seft-training
11 |  | 5 | WebDriver Commands | Browser Commands | 4 |  | Get knowledge baisc about web driver commands | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/browser-commands/
|  |  |  | Browser Navigation Commands | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/browser-navigation-commands/
|  |  |  | WebElement Commands | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/webelement-commands/
|  |  |  | FindElements Commands | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/findelement-and-findelements-command/
|  |  |  | Check Box & Radio buttons | 4 |  |  | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/checkbox-radio-button-operations/
|  |  |  | Drop Down & Multiple Selects | 4 |  |  | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/dropdown-multiple-select-operations/
|  |  |  | WebTable Handling | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/handle-dynamic-webtables-in-selenium-webdriver/
|  |  | Locators & Xpath | Use Of Browser Inspector | 4 |  | Get knowledge how to get the location of element | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/finding-elements-using-browser-inspector/
|  |  |  | FireBug & FirePath | 4 |  |  | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/xpath-firebug-firepath/
|  |  |  | Element Locator for WebDriver | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/webdriver-element-locator-firefox-add-on/
|  |  |  | XPath Helper Plug-in for Chrome | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/xpath-helper/
12 |  | 6 | Protractor | Install Protractor | 1 |  | Get knowledge Protractor | Seft-training
|  |  |  | Run simple demo on Protractor home page | 1 |  |  | Seft-training
|  |  |  | Protractor Locators | 6 |  |  | Seft-training
|  |  |  | Protractor API - browser | 4 |  |  | Seft-training
|  |  |  | Protractor API - element | 4 |  |  | Seft-training
|  |  |  | Protractor API - locator | 4 |  |  | Seft-training
|  |  |  | Develop some basic scripts by Protractor | 20 |  |  | Seft-training
|  | 7 | Final Report | Presentation of trained knowledge and demo | 40 |  | Understand and be able to work on the project | Seft-training
|  |  |  | Sum | 422 |  | hours
weeks (Count 6-8 hours/day,because Interns will join other training courses (English, Softskill))

## Automation Test (hidden)
Manual & Automation Testing Training Schedule
Week | Duration | Chapter | Training Outline | Content | Duration |  | Objectives | Training Method | Start date | Finish date | Progress | Notes
[5 empty] | Plan (hour) | Actual (hour)
1 |  | 1 | Software Testing Overview | Introduction to Software Testing | 2 |  | Get knowledge about basic theory of testing | Mentor |  |  |  | http://tryqa.com/ https://www.guru99.com https://www.tutorialspoint.com/software_testing/
|  |  |  | Objectives of Testing | 2 |  |  | Seft-training
|  |  |  | Software Development Process | 2 |  |  | Seft-training
|  |  |  | Principle of testing | 2 |  |  | Seft-training
|  |  |  | Error / Fault / Failure | 2 |  |  | Seft-training
|  |  |  | What is Verification & Validation | 2 |  |  | Seft-training
|  |  |  | Difference between QA & QC | 2 |  |  | Mentor
|  |  | Software Development Life Cycle (SDLC) | SDLC Phases | 2 |  | Understand the Agile model with the rest | Seft-training
|  |  |  | SDLC Models: Water Fall | 2 |  |  | Seft-training
|  |  |  | SDLC Models: V Model | 2 |  |  | Seft-training
|  |  |  | SDLC Models: Agile Model | 5 |  |  | Mentor
|  |  |  | Scrum Methodology | 5 |  |  | Mentor
|  |  |  | Kanban Methodology | 2 |  |  | Mentor
2 |  |  | Software Testing Type | Manual testing | 2 |  | Understand the testing type | Seft-training
|  |  |  | Automation testing | 2 |  |  | Seft-training
|  |  | Software Testing Methodologies | Static Testing | 2 |  | Understand the testing methodology | Seft-training
|  |  |  | Dynamic Testing | 2 |  |  | Seft-training
|  |  |  | White Box Testing | 2 |  |  | Seft-training
|  |  |  | Black Box Testing | 2 |  |  | Seft-training
|  |  |  | Gray Box Testing | 2 |  |  | Seft-training
|  |  |  | Presentation 1: Software Development Life Cycle, Software Testing Type, Software Testing Methodologies | 2 |  |  | Sharing meeting
3 |  | 2 | Software Testing Levels | Unit Testing | 4 |  | Understand the testing level | Seft-training
|  |  |  | Integration Testing | 4 |  |  | Seft-training
|  |  |  | System Testing | 8 |  |  | Mentor
|  |  |  | Acceptance Testing | 2 |  |  | Mentor
4 |  |  | Test case Design Technique | Specification-based techniques | 4 |  | Able to create testcase after read specs | Mentor
|  |  |  | Experience-based techniques. | 2 |  |  | Mentor
|  |  |  | Practice on real project: | 34 |  |  | Seft-training
|  |  |  | Presentation 2: Software Testing Levels, Test case Design Technique | 2 |  |  | Sharing meeting
5-6 |  | 3 | Basic Java for Tester | Data Types and Variables | 2 |  | Get basic knowledge about Java for Tester | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/data-types-variables/
|  |  |  | Operators | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/operators/
|  |  |  | Decision Making | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/decision-making/
|  |  |  | Arrays | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/arrays/
|  |  |  | Loops | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/loops/
|  |  |  | Classes and Objects | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/classes-objects/
|  |  |  | Class Constructors | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/class-constructors/
|  |  |  | String Class | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/string-class/
|  |  | Set Up Selenium WebDriver | Set Up Java | 0.5 |  | Setup environment and run 1st testcase on Firefox, Chrome | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/download-and-install-java/
|  |  |  | Set Up Eclipse | 0.5 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/download-and-start-eclipse/
|  |  |  | Set Up WebDriver Client | 1 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/download-selenium-webdriver-java-client/
|  |  |  | Configure Eclipse with WebDriver | 1 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/configure-eclipse-with-selenium-webdriver/
|  |  |  | First Test Case with FF Browser | 2 |  |  | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/first-test-case/
|  |  |  | Running Test on Chrome/IE Browser | 1 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/running-tests-in-chrome-browser/
|  |  | WebDriver Commands | Browser Commands | 4 |  | Get knowledge baisc about web driver commands | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/browser-commands/
|  |  |  | Browser Navigation Commands | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/browser-navigation-commands/
|  |  |  | WebElement Commands | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/webelement-commands/
|  |  |  | FindElements Commands | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/findelement-and-findelements-command/
|  |  |  | Check Box & Radio buttons | 4 |  | Get knowledge advangte about web driver commands | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/checkbox-radio-button-operations/
|  |  |  | Drop Down & Multiple Selects | 2 |  |  | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/dropdown-multiple-select-operations/
|  |  |  | WebTable Handling | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/handle-dynamic-webtables-in-selenium-webdriver/
|  |  | Locators & Xpath | Use Of Browser Inspector | 4 |  | Get knowledge how to get the location of element | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/finding-elements-using-browser-inspector/
|  |  |  | FireBug & FirePath | 4 |  |  | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/xpath-firebug-firepath/
|  |  |  | Element Locator for WebDriver | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/webdriver-element-locator-firefox-add-on/
|  |  |  | XPath Helper Plug-in for Chrome | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/xpath-helper/
|  |  | Page Object Model | Page Object Model | 14 |  | Get knowledge how to develop scripte by POM | Seft-training |  |  |  | https://www.toolsqa.com/selenium-webdriver/page-object-model/
|  |  |  | Presentation 3: Selenium WebDriver | 4 |  | Get knowledge how to develop scripte by POM | Seft-training |  |  |  | https://www.toolsqa.com/selenium-webdriver/page-object-model/
7 |  | 4 | TypeScript | What is Type Script? | 1 |  | Get knowledge TypeScript | Seft-training
|  |  |  | Install TypeScript | 1 |  |  | Seft-training
|  |  |  | TypeScript Basic Types | 6 |  |  | Seft-training
|  |  |  | If Else, and Switch Case in TypeScripts | 6 |  |  | Seft-training
|  |  |  | Loop in TypeScripts | 6 |  |  | Seft-training
|  |  |  | Class and object | 6 |  |  | Seft-training
|  |  |  | Async and await | 6 |  |  | Seft-training
8 |  | 5 | Protractor | Install Protractor | 1 |  | Get knowledge Protractor | Seft-training
|  |  |  | Run simple demo on Protractor home page | 1 |  |  | Seft-training
|  |  |  | Protractor Locators | 6 |  |  | Seft-training
|  |  |  | Protractor API - browser | 4 |  |  | Seft-training
|  |  |  | Protractor API - element | 4 |  |  | Seft-training
|  |  |  | Protractor API - locator | 4 |  |  | Seft-training
|  |  |  | Develop some basic scripts by Protractor | 20 |  |  | Seft-training
9-11 |  | 6 | Source Tree | Setup Source Tree | 2 |  |  | Seft-training
|  |  |  | Create branch | 2 |  |  | Seft-training
|  |  |  | Execute Pull, Push, Commit | 2 |  |  | Seft-training
|  |  |  | Create Merge Request | 2 |  |  | Seft-training
|  |  | Scripting Protractor | Develop testscript based on Manual Testcase | 112 |  |  | Seft-training
12 |  | 7 | Final Report | Presentation of trained knowledge and demo | 40 |  | Understand and be able to work on the project | Seft-training
|  |  |  | Sum | 420 |  | hours
weeks (Count 6-8 hours/day,because Interns will join other training courses (English, Softskill))

## Enroll- Course X (hidden)
No | Name | Subject | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Archivement | Note
1 | Nguyễn Van A | #REF! | x | [24 empty] | Create a website with header, title, body, Img tag…

## Sheet1 (hidden)
No | Name | Subject
1 | Nguyễn Van A

## Automation Test2 (hidden)
No. | Training Outline | Content | Duration |  | Objectives | Training Method | Start date | Finish date | Progress | Notes
|  |  | Plan | Actual
Selenium - Web Browser Automation |  |  | 6 weeks
1 | Basic Java for Tester | Data Types and Variables | 2 |  | Get basic knowledge about Java for Tester | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/data-types-variables/
2 |  | Operators | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/operators/
3 |  | Decision Making | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/decision-making/
4 |  | Arrays | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/arrays/
5 |  | Loops | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/loops/
6 |  | Classes and Objects | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/classes-objects/
7 |  | Class Constructors | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/class-constructors/
8 |  | String Class | 2 |  |  | Seft-training |  |  |  | http://toolsqa.com/java/basic-java-programming/string-class/
9 | Set Up Selenium WebDriver | Set Up Java | 1 |  | Setup environment and run 1st testcase on Firefox, Chrome | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/download-and-install-java/
10 |  | Set Up Eclipse | 1 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/download-and-start-eclipse/
11 |  | Set Up WebDriver Client | 1 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/download-selenium-webdriver-java-client/
12 |  | Configure Eclipse with WebDriver | 1 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/configure-eclipse-with-selenium-webdriver/
13 |  | First Test Case with FF Browser | 2 |  |  | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/first-test-case/
14 |  | Running Test on Chrome/IE Browser | 1 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/running-tests-in-chrome-browser/
15 | WebDriver Commands | Browser Commands | 4 |  | Get knowledge baisc about web driver commands | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/browser-commands/
16 |  | Browser Navigation Commands | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/browser-navigation-commands/
17 |  | WebElement Commands | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/webelement-commands/
18 |  | FindElements Commands | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/findelement-and-findelements-command/
After 2 weeks | Presentation | Run simple testcase on Login screen | 8 |  |  | Sharing meeting
19 | WebDriver Commands | Check Box & Radio buttons | 4 |  | Get knowledge advangte about web driver commands | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/checkbox-radio-button-operations/
20 |  | Drop Down & Multiple Selects | 4 |  |  | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/dropdown-multiple-select-operations/
21 |  | WebTable Handling | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/handle-dynamic-webtables-in-selenium-webdriver/
22 | Locators & Xpath | Use Of Browser Inspector | 4 |  | Get knowledge how to get the location of element | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/finding-elements-using-browser-inspector/
23 |  | FireBug & FirePath | 4 |  |  | Mentor |  |  |  | http://toolsqa.com/selenium-webdriver/xpath-firebug-firepath/
24 |  | Element Locator for WebDriver | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/webdriver-element-locator-firefox-add-on/
25 |  | XPath Helper Plug-in for Chrome | 4 |  |  | Seft-training |  |  |  | http://toolsqa.com/selenium-webdriver/xpath-helper/
26 | Switches Alerts & Windows | Wait Commands | 4 |  | Get knowledge how to handle the alert and waiting for element displays | Mentor
27 |  | Smart Waits | 4 |  |  | Seft-training
28 |  | Switch Commands | 4 |  |  | Seft-training
29 |  | Handling Alerts | 4 |  |  | Seft-training
30 |  | Different types of Alerts | 4 |  |  | Mentor
31 |  | Handling Multiple Windows | 4 |  |  | Seft-training
After 2 weeks | Presentation | Run script based on testcase without framework | 8 |  |  | Sharing meeting
32 | TestNG Automation Framework | Install TestNG | 4 |  | Write script based on TestNG Automation Framework | Seft-training
33 |  | First Test Case with TestNG | 4 |  |  | Mentor
34 |  | TestNG Test Suite | 4 |  |  | Seft-training
35 |  | Annotations, Groups & DependOn | 4 |  |  | Seft-training
36 |  | Test Cases Prioritizing & Sequencing | 4 |  |  | Seft-training
37 |  | TestNG Reporters & Asserts | 4 |  |  | Seft-training
38 |  | TestNG Parameters & Data Provider | 4 |  |  | Seft-training
39 |  | TestNG DataProvider with Excel | 4 |  |  | Mentor
40 | Hybrid Automation Framework | Page Object Model | 4 |  | Write script based on Hybird Automation Framework | Mentor
41 |  | Modular Driven Framework | 4 |  |  | Seft-training
42 |  | Functions Parameters | 4 |  |  | Seft-training
43 |  | Constant Variables | 4 |  |  | Seft-training
44 |  | Data Driven Framework | 4 |  |  | Mentor
45 |  | TestNG Reporting | 4 |  |  | Seft-training
46 |  | Hybrid Automation Framework | 4 |  |  | Seft-training
After 2 weeks | Presentation | Run script based on testcase with Hybird framework | 8 |  |  | Sharing meeting
47 | Appium Tutorial | Install the Java Development Kit (JDK) | 2 |  | Setup environment for Appium | Seft-training
48 |  | Set Up Java Environment Variable Path | 2 |  |  | Seft-training
49 |  | Install Android SDK / ADB on Windows | 2 |  |  | Seft-training
50 |  | Install Android SDK Packages | 2 |  |  | Seft-training
51 |  | Set up Android Environment Variable | 2 |  |  | Seft-training
52 |  | Download and Install NodeJs | 2 |  |  | Seft-training
53 |  | Install Microsoft .net Framework | 2 |  |  | Seft-training
54 |  | Download And Install Appium Desktop Client | 2 |  |  | Seft-training
55 |  | Enabling Developer Mode Options on Android Phone or Tablet | 2 |  |  | Seft-training
56 |  | Install PdaNet to Connect with Android Device | 2 |  |  | Seft-training
57 |  | Install Eclipse IDE And Set up a Project | 2 |  |  | Seft-training
58 |  | Set Up Appium Project in Eclipse | 2 |  |  | Seft-training
59 |  | First Appium Test to Launch Amazon App | 2 |  |  | Mentor
60 | Appium Basics | How to use Appium UIAutomatorViewer | 4 |  | Get knowledge how to find location on Mobile and store it on Hybird framework | Mentor
61 |  | How to use Locators in Appium | 4 |  |  | Mentor
62 |  | Inspect elements of Mobile Web Application | 4 |  |  | Mentor
63 |  | How to Inspect and Automate WebView in Hybrid App | 4 |  |  | Mentor
Finish course | Presentation | Run simple script on Mobile | 8 |  |  | Sharing meeting